F. Willeke , MHE									4.September 2000

HERA Report

HERA –Experiments Coordination Meeting

September 4 2000

Run2000

Major Results, Achievements, Problems

Very smooth and efficient running with high luminosity (exceeding the design value) and

Polarization.

LUMINOSITY:	Record Peak :  2 x 1031 cm-2 sec-1  (design 1.5 x 1031 cm-2 sec-1  )

Record Spec.:	8 x 1029 mA-2cm-2 sec-1

Integrated: 	66.6 pb-1

BEAM CURRENTS: 	Protons, peak: 	> 100mA

Positrons	> 50mA

SPIN POLARIZATION:	Record 65%, Routine (50-60)%

EFFICIENCY:		56%

MACHINE PHYSICS

Coasting Beam: Improved (I dc –I b<0.5mA) due to coasting beam kicker and optimized rf parameters, Production mechanism still under study.

Tail Shaping: progress and improvements

Longitudinal Stability: Still a factor of 4 in blowup during acceleration, good progress in diagnostics

Beam-Beam: Limits explored, far from present parameters

TECHNICAL Performance 		No major  problems

AUGUST ACCELERATOR STUDIES:

Important Result:

- 72 degree e- Beam optics for 2001 verified, no problems with emittance, aperture and spin polarization  (61% achieved even with shifted RF frequency)

- Tools for 2001 recommissioning tested and checked

- Improved diagnostics tested

- Dynamic aperture p-ring remeasured

- Beam Echo measurements performed

- Synchrotron Radiation Suppression p-ring  studied

- e- Beam-beam limits explored

Luminosity Upgrade Status

Superconducting Magnets:

GO#1 delivered to DESY, being tested, field quality ok, magnet performance ok, quench protection not yet tested, cryogenic performance poor,

Water condensation problem can be solved by insulating the cryostat at the outside.

GO# 2 should have improved cryogenic properties, it is expected to arrive by mid September at DESY.

GO#3 coil curing in progress.

GG#1: Coil successfully tested in vertical Dewar, performance is good. (500A reached).

Normal Conducting Magnets:

Available, stray field measurements in progress,

Supports, Girders, Bridges:

Bridges equipped with magnets, power test performed, warming-up little (5 degree), 0.3mm magnet movements observed

Vacuum System:

One right-side  vacuum system 4mm-18m complete, installed in the magnets on bridge, pumped down, no leaks, other systems:  normal progress, they will be available

Diagnostics systems

are on schedule, they will be available.

First Thoughts on Upgrade Recommissioning

Start up 				(        -2 weeks per ring =4 weeks ==>   Sum = 4 weeks

with detectors turned off

Rotators N, S flat (on in the East)

-First turn steering, beam, store beam, correct orbits

-Checking new and old components with beam

-Check out diagnostics, beam dump, quench protection, bpms, SR monitoring, temperature monitoring

Explore optics and aperture,		 (	 1 week per ring =2weeks  ==> 	Sum = 6 weeks

with detectors turned off

Rotators N, S flat (on in the East)

Extensive studies in both rings at several energies

Aperture scans

Turn on detector fields, 			( 			3 weeks  ==>	 S = 9 weeks

Learn how SC magnets are behaving,

Learn   ramping with corrections for motion of S.C. magnets,

remeasure optics,

learn how to decouple the  machines

Collide beams, 				( 			2 weeks  ==> 	 S = 11 weeks

-optimize machine parameters (orbit, beam height, working points etc)

-explore optimum luminosity parameters

-luminosity scans

Investigate Synchrotron Radiation, 	( 			2 weeks  ==> 	 S = 13 weeks

-Study beam position and SR positions in the IR

-Test special correction procedures including the bridges

Perform luminosity (days)		( 			4 weeks    ==>	 S = 17 weeks

-Runs with exp.’s on to check on backgrounds

In parallel: Tune Polarization for HERMES in dedicated shifts (nights)

With ZEUS/H1 solenoids down N S Rotators flat (HERA-B running possible)

(a) During days, b) at nights? Ramp down/up solenoids frequently?)

Turn on south/North rotators, 		( 			 2 weeks    ==>	S=19 weeks

Orbit, optic check,

Set up luminosity

Luminosity running 			(                      	 	8 weeks     ==>   S=27 weeks

with frequent machine studies

To set up polarization with detector fields on

(Start with detectors off, ramp them up bit by

bit, retune....

Goal: Start normal running with long. Polarization at N,S,E in January 2002.

Luminosity Monitors needed   mid August

Detectors needed September 1st.

| HERA PARAMETERS RUN 2001 (proposed/expected) |  |  |  |
| --- | --- | --- | --- |
| Particles |  | Protons | Positrons |
| Beam Energies | [GeV] | 920 | 27.52 |
| Total Beam Currents | [mA] | 90 | 20-40 |
| Emittances | [nm] | 5 | 22 |
| Beta functions x | [m] | 2.45 | 0.6 |
| y | [m] | 0.2 | 0.25 |
| Initial Luminosity | [1031cm-2sec-1] | (1.5-3.5) |  |
| Efficiency | [%] | 40% |  |
| Run Time | [days] | 80 |  |
| Integrated Luminosity | [pb-1] | 20-40 |  |