F. Willeke

-MHE-

# HERA-Experiments Coordination Meeting

## January 12, 2001

### HERA UPDATE

- Status of Components

- Status of installation

- Revised Schedule of the Commissioning

#### Delivery/Manufactury  of Components

##### Superconducting Magnets Delivery dates:

##### GO#2 & #3  available

GO#4   	April 12 2001 (spare)

GG#1 	Febr 16      (assembly in progress)

GG#2		Febr 22       (start assemby Jan 15)

GG#3		March 22 (spare)

###### Cryogenic Supplies for GG/GO

Coldbox ZEUS delivery on Jan 26.

Coldbox H1 delivery on Feb 7  (4 week delay due to damage during manufacturing)

Impact on the schedule: hopefully none, cold test H1 still planned for March 14

###### Power Supplies

###### The chopper supplies will be delayed by 4 weeks

Impact on the schedule:  none

Vacuum System

Last critical item: GM chambers (p, γ)

Two chambers completed, tested, ok, the rest will be in time

Absorber 4 (crotch absorber):  Braising failed at the DESY shops,

(all braised parts machined-off, braising will restart next week

4 weeks delay, hopefully no impact on the schedule, but logistics difficult

###### QR-Coils

A probem was found last Tuesday on the insulation: All new coil need additional work, 14 QR magnets. Need to be de-installed again

Impact on the schedule: not yet clear

GO MILESTONES as of 9 Jan 2001

| Scheduled DATE | Actual / Estimated DATE | DESCRIPTION |
| --- | --- | --- |
| 3/1/98 | 3/1/98 | Start Program |
| 8/21/98 | 8/31/99 | Finish Q0 Magnet Design |
| 8/21/98 | 12/3/98 | Finish Wiring Machine Design |
| 9/29/98 | 10/6/99 | Finish Cold Mass Tooling Design |
| 11/17/98 | n/a | Finish Magnetic Measurement Equipment Design |
| 11/19/98 | 5/21/99 | Receive Superconductor |
| 1/20/99 | 7/2/99 | Finish Wiring Machine Installation |
| 1/20/99 | 10/1/99 | Receive Magnet Parts |
| 1/28/99 | 7/2/99 | Finish Coil Tooling Installation |
| 2/3/99 | 9/22/99 | Finish Cryostat Tooling Design |
| 3/18/99 | 9/2/99 | Finish Q0 Test Coil Assembly |
| 4/16/99 | 7/16/99 | Start G0 Magnet #1 Production |
| 5/14/99 | 8/31/99 | Start G0 Magnet #2 Production |
| 6/14/99 | 10/21/99 | Start G0 Magnet #3 Production |
| 8/17/99 | 4/12/01 | Finish G0 Magnet #4 Production |
| 8/31/99 | 6/22/00 | Finish G0 Magnet #2 Production |
| 9/15/99 | 10/11/00 | Finish G0 Magnet #3 Production |

GG MILESTONES as of 9 Jan 2001

| SCHEDULED DATE | Actual / Estimated Date | DESCRIPTION |
| --- | --- | --- |
| 4/1/98 | 4/1/98 | Start Program |
| 9/1/98 | 2/2/00 | Finish GG Magnet Design |
| 6/18/99 | 4/13/00 | Receive Magnet Parts |
| 4/15/99 | 11/19/99 | Finish GG Test Coil Assembly |
| 7/14/99 | 12/6/99 | Start GG Magnet #1 Production |
| 9/9/99 | 12/27/99 | Start GG Magnet #2 Production |
| 11/4/99 | 12/29/99 | Start GG Magnet #3 Production |
| 12/10/99 | 2/16/01 | Finish GG Magnet #1 Production |
| 2/10/00 | 2/22/01 | Finish GG Magnet #2 Production |
| 4/7/00 | 3/22/01 | Finish GG Magnet #3 Production |

Progress of Installation

QR Magnet Coil Replacement

Has been finished WL,WR, OL, OR, must be repeated!

###### Luminosity Upgrade

Fully Equipped Magnet Bridges installed		NL, NR, SL, SR, 	ok!

GM-Magnets in place					NL, NR, SL, SR, 	ok!

Magnet supports completed				NR, NL

Magnet pedestals modified, placed			SR, SL,

Magnet Installation NR  has started,  1BQ, 3GN	almost within plan

(1 week delay due to non-planned survey)

Magnet Cabling, Signal Cabling ,water connection more or less within schedule

Rotator Installation

Movable Magnet Supports NR finished, tested, ready for magnets to be installed

Movable Magnet Supports NL in progress (behind schedule)

| HERA | Run | 2001 |  |
| --- | --- | --- | --- |
| HERA Schedule 2001 updated | 1/11/01 17:21 |  |  |
|  | Begin | Duration/Days | End |
| Startup 2001 | 18-Jun-01 | 1 | 19-Jun-01 |
| Establish Beam Operation | 18-Jun-01 | 22 | 10-Jul-01 |
| Maintenance day *) | 10-Jul-01 | 1 | 11-Jul-01 |
| Explore Optics | 11-Jul-01 | 23 | 3-Aug-01 |
| Turn-On Detector Fields | 3-Aug-01 | 18 | 21-Aug-01 |
| Maintenance day*) | 21-Aug-01 | 1 | 22-Aug-01 |
| Set up & Optimize Collisions | 22-Aug-01 | 12 | 3-Sep-01 |
| Investigate Synchrotron Radiation | 3-Sep-01 | 15 | 18-Sep-01 |
| Maintenance day*) | 18-Sep-01 | 1 | 19-Sep-01 |
| First Luminosity Runs | 19-Sep-01 | 21 | 10-Oct-01 |
| Polarization Tuning | 10-Oct-01 | 7 | 17-Oct-01 |
| Turn on North /South rotators | 17-Oct-01 | 19 | 5-Nov-01 |
| Break for Experiments | 5-Nov-01 | 3 | 8-Nov-01 |
| Luminosity Run | 8-Nov-01 | 32 | 10-Dec-01 |
| Polarization Tuning | 10-Dec-01 | 12 | 22-Dec-01 |
| Maintenance Period | 22-Dec-01 | 11 | 2-Jan-02 |
| Restart | 2-Jan-02 | 14 | 16-Jan-02 |
| *) if needed |  |  |  |